## Sheet1
Thurston/Mason System of Care Partnership (FYSPRT) Work Plan - January 2021 through December 2022
Work Item | Goal | Start Date | Target Timeline | Assignments | Barriers/Challenges & Solutions | Completion Dates
Behavioral Health 2021-Thurston/Mason Behavioral Health Services Matrix | This item that was originally started as a standing work item in 2020 has been used to provide time to ask questions about changes brought about by integration and the structural changes to the mental health system. The matrix was created to show the services available during and after integration. | 2020-03-27 | 2021-01-22 | Assigned to the TMBHASO, Amy Martin | Barrier: Only one MCO agreed to share information about providers/services covered. Solution: Add statement advising families to contact their MCO about coverage. | 2021-01-22
Behavioral Health Assessments Guide | Create a family friendly behavioral health assessments guide. | 2020-01-24 | 2/26/2021 -Document in English 3/23/2021 - Document in Spanish | Assigned to a workgroup with parents and professionals: Dena Wagner, Jacque Ward, Mya Hernandez, Philip Compton, Alicia Ferris, Sara Ellsworth and Gary Enns | Challenge: Determine how to include all types of assessments without overwhelming detail in an overly lengthy document. Solution: Create a team where parents are in the majority and part of the workgroup from the beginning, to make sure the document is family friendly. Check-ins with the youth/family group and with the SOCP to advise the workgroup as to whether they are on the right path. | 2021-03-23
Behavioral Health Assessments - Improved availability of school based services. | Track school-based behavioral health services seen as a pathway to assessments. | 2020-01-24 | 3/23/2021 - On hold due to pandemic. | Assigned to and updates sought from Behavioral Health Resources; Educational Services District 113; Consejo Counseling; SeaMar Behavioral Health Services; North Thurston Public Schools. | Challenge: The pandemic has created challenges due to limits with in-person services. Solution: Updates to Behavioral Health in Schools spreadsheet by providers until March 2021 SOCP meeting when participants decided it would be best to put this document on hold until students were back in school.
Increase representation of marginalized populations. | Increased use of culturally competent strategies for outreach to historically marginalized populations for participation in the SOCP. | 2020-08-28 | On-going: The tri-leads and some parents want to continue this outreach until there is consistent participation. | Assigned to Dena Wagner for Hispanic/Latino organization in Mason county; Jacque Ward for Black representation; Alicia Ferris for Native American/Regional Indian Tribes participation. Additionally, two parents volunteered to represent survivors of domestic violence and the protected population. The convener recruited a young adult who wanted to represent LGBTQIA, houseless and survivors of suicide populations. | Challenge: Maintain consistent participation by tribes especially for the Nisqually Indian Tribe. Also to maintain consistent participation by other individuals and organizations that represent marginalized populations. Solution: The convener is contacting individuals and participants that represent organizations between monthly meetings to let them know that we missed them. This has resulted in building a rapport and finding that we may need to invite the person who will assign others to attend meetings. It has also been helpful, mostly with the Skokomish Indian Tribe, to be responsive to calls for help in connecting youth/families to services.
Youth Recruitment |  | 2020-08-11 | On-going: The youth tri-leads want this outreach to continue until there is consistent participation. | Assigned to Sebastian Compton and Emily Rogers and technical assistance from National Youth Move. | Challenge: Providing a safe and comfortable space online for youth to discuss issues with access to services and needs/strengths of the system. Solution: A youth tri-lead hosts a monthly Zoom meeting for youth with technical support from the convener. Youth are supported by their parents at monthly FYSPRT meetings. Both youth tri-leads have active roles in the monthly FYSPRT meetings. One of the Youth Tri-leads is building a website for youth to use for commentary.
Crisis services and warm handoffs after receiving crisis services. |  | 2021-04-23 | Plan Pending-Area of Focus/Work Item chosen by a vote of participants in April and a 5-step wraparound process started and will be completed with a plan n place by 5/28/21. | To be determined on 5/28/21 at the monthly System of Care Partnership meeting. | Challenge: Get results of votes for top two needs from the list provided by participants. Solution: Develop strategies and create a plan during the 5/28/21 System of Care Partnership meeting