## Sheet1
Thurston/Mason System of Care Partnership (FYSPRT) Work Plan - January 2021 through December 2022
Goals | Action Steps | Those Assigned | Timeline for Completion
Increase representation of marginalized populations by Increasing use of culturally competent strategies for outreach to historically marginalized populations for participation in the SOCP. | 1. Send invitations and agendas to Native American Tribes within the region, i.e. Skokomish Indian Tribe, Squaxin Island Tribe and Nisqually Indian Tribe. Contact any Tribal representative to let them know they are missed if they are not present at a monthly SOCP meeting. 2. Support current participants who are people of color, participants who identify as LGBTQIA2S+, people who are houseless or organizations who support people who are houseless, with invitations and contact between meetings. 3. Support individuals with disabilities with any accommodations necessary to assure participation in monthly SOCP meetings. 4. Provide meeting setting accommodations and additional contact for marginalized populations who are in Tri-lead positions. 5. Continue recruitment of marginalized population representatives. | Convener/Donna Obermeyer, Cherise Meier and Kimberley Miller | Start date was 8/28/2020 and this is on-going throughout 2023 and 2024 until there is consistent participation.
Increase youth recruitment and participation in the System of Care Partnership. | 1. Send invitations and agendas to youth and young adults for monthly SOCP meetings. Creation of social media mental health platform by youth to assure youth voice is heard, to include continuous monitoring and regular report-outs during monthly SOCP meetings. 2. Encourage youth/young adults to participate as Tri-leads. | Xana Caillouet, Brandi Kinston, Emily Lockhart and Spencer McQuilkin | The start date was 8/11/2020 and will continue through 2023 and 2024 until youth/young adults, Tri-leads and the SOCP are satisfied that there is a robust level of participation.
Over-arching goal: More mental health awareness and fluency taught in schools, to parents and to staff. The Ending the Silence presentation with NAMI Mason/Thurston is a good starting point. | 1. Identify school programs being implemented in local districts to include a presentation by the ESD Behavioral Health Navigator. 2. Host NAMI's Ending the Silence presentation. 3. Brainstorming to create ideas for subgoals. | Sara Ellsworth , Eliana Stockwell-Ferber, Dena Wagner & Heidi Knadel | 2023-01-13
Subgoal A: Opportunities for youth to volunteer with other students to help - everyone learns and this provides mentorship opportunities for students. Matching students based on strengths and needs - pairing a youth with great ability to manage their energy, for example, with with student who needs additional skills in this area. Students to be able to mentor students at other schools. | 1. Identification of strategies. 2. Possible vote on strategies. | SOCP Participants | 2023-02-24
Subgoal B: Mental health initiatives at schools to create/inform around mental health needs - student driven and led (SOCP do the initiative?) | 1. Identification of strategies. 2. Possible vote on strategies. | SOCP Participants | 2023-02-24
Subgoal C: Classes do an activity that elicits ideas from students - what can we do better/change? Anonymous notes. Consider providing incentives like gift cards for small amounts. | 1. Identification of strategies. 2. Possible vote on strategies. | SOCP Participants | 2023-02-24