## Sheet1
Thurston/Mason System of Care Partnership (FYSPRT) Work Plan - January 2021 through December 2022
Goals | Action Steps | Those Assigned | Timeline for Completion
Increase representation of marginalized populations by Increasing use of culturally competent strategies for outreach to historically marginalized populations for participation in the SOCP. | 1. Send invitations and agendas to Native American Tribes within the region, i.e. Skokomish Indian Tribe, Squaxin Island Tribe and Nisqually Indian Tribe. Contact any Tribal representative to let them know they are missed if they are not present at a monthly SOCP meeting. 2. Support current participants who are people of color, participants who identify as LGBTQIA2S+, people who are houseless or organizations who support people who are houseless, with invitations and contact between meetings. 3. Support individuals with disabilities with any accommodations necessary to assure participation in monthly SOCP meetings. 4. Provide meeting setting accommodations and additional contact for marginalized populations who are in Tri-lead positions. 5. Continue recruitment of marginalized population representatives. | Convener/Donna Obermeyer, Cherise Meier, Kimberley Miller, Skokomish Tribe representative and Peter Ansera, Executive Director, Nisqually Tribe. | May 2023 Update: Outreach to Kimberley Miller, Skokomish Tribe, to contact Squaxin Island Tribe representative Charlene Abrahamson, in addition to direct contact by convener and contact with Peter Ansera, Nisqually Tribe. Parent and minority-owned small business/non-profit, participated in the May meeting. We continue to have LGBTQIA2S+ representation in our group and leadership and participation at the May SOCP meeting.
Increase youth recruitment and participation in the System of Care Partnership. | 1. Send invitations and agendas to youth and young adults for monthly SOCP meetings. Creation of social media mental health platform by youth to assure youth voice is heard, to include continuous monitoring and regular report-outs during monthly SOCP meetings. 2. Encourage youth/young adults to participate as Tri-leads. 3. Consult with Youth Move National and share their youth engagement webinars. 4. Invite youth to meet in person or on Zoom to determine participation barriers. | Xana Caillouet, Brandi Kinston, Dena Wagner, Donna Obermeyer, Alexandra Jacobsonnn | May 2023 Update: A Co-System Tri-lead recruited a new Youth Tri-lead and they received unanimous support from the SOCP at the May meeting. This youth is a certified peer counselor who has pledged to mentor and encourage youth voice.
Over-arching goal: More mental health awareness and fluency taught in schools, to parents and to staff. The Ending the Silence presentation with NAMI Mason/Thurston is a good starting point. | 1. Identify school programs being implemented in local districts to include a presentation by the ESD Behavioral Health Navigator. 2. Host NAMI's Ending the Silence presentation. 3. Brainstorming to create ideas for subgoals. 4. Brainstorming to create strategies for each subgoal. 5. Review strategies and vote for one strategy for each subgoal. 6. Share vote results and discuss next steps. 7. Create workgroup to work on strategies and implementation. | SOCP parents and system participants workgroup volunteers including Shelton, North Thurston and Olympia school districts, Catholic Community Services, Behavioral Health Resources, Thurston parents - Brandi Kingston and Philip Compton, Mason parents Jacque Ward and Dena Wagner. | May 2023 Update: The workgroup was launched on 5/12/23 and included parents and school districts. Educational Service District 113 is to be invited to all future meetings as determined at the SOCP May meeting on 5/26/23.
Subgoal A: Opportunities for youth to volunteer with other students to help - everyone learns and this provides mentorship opportunities for students. Matching students based on strengths and needs - pairing a youth with great ability to manage their energy, for example, with with student who needs additional skills in this area. Students to be able to mentor students at other schools. | 1. Share strategy vote results and ask the group if they want to break the tie for the two items receiving the most votes (A2 and A4). 2. Discuss next steps including forming an implementaton workgroup. 3. | SOCP parents and system participants workgroup volunteers including Shelton, North Thurston and Olympia school districts, Catholic Community Services, Behavioral Health Resources, Thurston parents - Brandi Kingston and Philip Compton, Mason parents Jacque Ward and Dena Wagner. | May 2023 Update: The SOCP decided to keep A2 and A4, formed a workgroup and the workgroup met on 5/12/23. The Co-System Tri-lead facilitating the workgroup provided an update at the 5/26/23 meeting.
Subgoal B: Mental health initiatives at schools to create/inform around mental health needs - student driven and led (SOCP do the initiative?) | 1. Share strategy vote results. 2. Discuss next steps including forming an implementation workgroup. | SOCP parents and system participants workgroup volunteers including Shelton, North Thurston and Olympia school districts, Catholic Community Services, Behavioral Health Resources, Thurston parents - Brandi Kingston and Philip Compton, Mason parents Jacque Ward and Dena Wagner. | May 2023 Update: The SOCP voted for strategy B2, formed a workgroup and the workgroup met on 5/12/23. The Co-System Tri-lead facilitating the workgroup provided an update at the 5/26/23 meeting.
Subgoal C: Classes do an activity that elicits ideas from students - what can we do better/change? Anonymous notes. Consider providing incentives like gift cards for small amounts. | 1. Share strategy vote results. Discuss next steps including forming an implementation workgroup. | SOCP parents and system participants workgroup volunteers including Shelton, North Thurston and Olympia school districts, Catholic Community Services, Behavioral Health Resources, Thurston parents - Brandi Kingston and Philip Compton, Mason parents Jacque Ward and Dena Wagner. | May 2023 Update: The SOCP voted for strategy C3, formed a workgroup and the workgroup met on 5/12/23. The Co-System Tri-lead facilitating the workgroup provided an update at the 5/26/23 meeting.