## Sheet1
Thurston/Mason System of Care Partnership (FYSPRT) Work Plan - January 2021 through December 2022
Work Item | Goal | Start Date | Target Timeline | Assignments | Barriers/Challenges & Solutions | Completion Dates
Behavioral Health 2021-Thurston/Mason Behavioral Health Services Matrix | This item that was originally started as a standing work item in 2020 has been used to provide time to ask questions about changes brought about by integration and the structural changes to the mental health system. The matrix was created to show the services available during and after integration. | 2020-03-27 | 1/22/2021 Completed in the first quarter of 2021 | Assigned to the TMBHASO, Amy Martin | Barrier: Only one MCO agreed to share information about providers/services covered. Solution: Add statement advising families to contact their MCO about coverage. | Completed as of 1/22/2021
Behavioral Health Assessments Guide | Create a family friendly behavioral health assessments guide. | 2020-01-24 | 2/26/2021 -Document in English 3/23/2021 - Document in Spanish Completed in the first quarter of 2021. | Assigned to a workgroup with parents and professionals: Dena Wagner, Jacque Ward, Mya Hernandez, Philip Compton, Alicia Ferris, Sara Ellsworth and Gary Enns | Challenge: Determine how to include all types of assessments without overwhelming detail in an overly lengthy document. Solution: Create a team where parents are in the majority and part of the workgroup from the beginning, to make sure the document is family friendly. Check-ins with the youth/family group and with the SOCP to advise the workgroup as to whether they are on the right path. | Completed as of 3/23/2021
Behavioral Health Assessments - Improved availability of school based services. | Track school-based behavioral health services seen as a pathway to assessments. | 2020-01-24 | 3/23/2021 - On hold due to pandemic. | Assigned to and updates sought from Behavioral Health Resources; Educational Services District 113; Consejo Counseling; SeaMar Behavioral Health Services; North Thurston Public Schools. | Challenge: The pandemic has created challenges due to limits with in-person services with the exception of ESD 113. Gaps for youth who are not Medicaid eligible; gaps for elementary schools and gaps in coverage for all districts in the region. Solution: Updates to Behavioral Health in Schools spreadsheet by providers until March 2021 SOCP meeting when participants decided it would be best to put this document on hold until students were back in school. However, the providers including ESD 113 have been updating the group during Share Time at meetings or in response to parent questions/discussions at meetings about services in schools and that started in the Fall of 2021. 3/31/22: A majority of votes for an item (Area of Focus) related to this goal may help improve access to assessments. This item was added as a result of a new survey and needs assessment, is in the lead and likely to be announced at the April 2022 SOCP meeting: h) More mental health awareness and fluency taught in schools, to parents and to staff. The Ending the Silence presentation with NAMI Mason/Thurston is a good starting point.*
Increase representation of marginalized populations. | Increased use of culturally competent strategies for outreach to historically marginalized populations for participation in the SOCP. | 2020-08-28 | On-going: The tri-leads and some parents want to continue this outreach until there is consistent participation. | Assigned to Dena Wagner for Hispanic/Latino organization in Mason county; Jacque Ward for Black representation; Alicia Ferris for Native American/Regional Indian Tribes participation. Additionally, two parents volunteered to represent survivors of domestic violence and the protected population. The convener recruited a young adult who wanted to represent LGBTQIA, houseless and survivors of suicide populations. When this individual was no longer able to participate, the convener asked a parent who is an ally/advocate for this population and she accepted and will answer anyone's questions or find answers quickly if she is unable to answer them. One of the Family Tri-leads is multi-racial (Black, White & Native American) and there are two Black systems participants, one for a school district and one for Juvenile Rehabiliation. | Challenges: Maintain consistent participation by tribes especially for the Nisqually Indian Tribe. A challenge in 2021 has been that the Tribe shut down their behavioral health services and then hired a consultant to restructure/rebuild these services. During the last quarter of 2021 the consultant was contacted and asked for a call back in 2022. There have been efforts to maintain consistent participation by other individuals and organizations/individuals that represent marginalized populations. A Migrant Re-engagement specialist who participates in Mason county community meetings (consortium) has been added to the roster, but has not been attending and this could be because of the large areas of the state he covers. A strong African American parent who advocates for the needs of Black youth and families with regard to equality/equity and culturally appropriate behavioral health services has been added to the roster and participated in the December 2021 meeting but future attendance will likely rest on her schedule (kids/running a non-profit/school) and if SOCP is relevant enough to make meetings a priority. Cielo has been very busy serving youth/families and attend as available. Solutions: The convener is contacting individuals and participants that represent organizations between monthly meetings to let them know that we missed them. This has resulted in building a rapport and finding that we may need to invite the person who will assign others to attend meetings. It has also been helpful, mostly with the Skokomish Indian Tribe, to be responsive to calls for help in connecting youth/families to services. Cielo responded to a recent check-in and confirmed they want to be kept on the roster to receive invitations and will attend as available. | 9/23/22 The Squaxin Island Tribe and Skokomish Tribe participated during the third quarter. A parent with lived experience, racial/ethnic diversity and impaired vision was added to the roster and participated during the third quarter. Our Ark, a non-profit that helps youth living on the streets of Thurston county has continued to participate in meetings. Progress towards completion: As of 10/1/2021 our FYSPRT has consistent LGBTQIA+ Ally/Advocate voice at meetings; consistent participant by two Tribes - Skokomish Indian Tribe and Squaxin Island Tribe - at least once a quarter; consistent participation of non-white participants from a school district and Juvenile Rehabilitation; consistent leadership/facilitation as a Family Tri-lead who is multi-racial (Black, White, Native American). 3/31/22: The Wa He Lut Indian school counselor has been added to the roster. Also, one of the youth participants on the SOCP who identifies as transgender sent an interest statement for a Youth Tri-lead position. In addition another youth was added to the roster in the first quarter of 2022, increasing the SOCP youth identifying as LGBTQIA+ to three as well as supportive parent allies.
Youth Recruitment | Increase youth participation in the System of Care Partnership. | 2020-08-11 | On-going: The youth tri-leads want this outreach to continue until there is consistent participation. | Assigned to Sebastian Compton with technical assistance from National Youth Move and support (Zoom) from convener. Convenver recruited two additional youth for the youth-only monthly meetings in September 2021. | Challenge: Providing a safe and comfortable space online for youth to discuss issues with access to services and needs/strengths of the system. Engagement needs for these gatherings; more youth leaders with time to keep up consistent communication with other youth; Zoom fatigue; time constraints due to school and youth with behavioral health needs often involved with WISe. Solution: A youth from the SOCP created and offered to share an Instagram link about youth voice for mental health during the third quarter.A youth tri-lead hosts a monthly Zoom meeting for youth with technical support from the convener. Youth are supported by their parents at monthly FYSPRT meetings. Both youth tri-leads have active roles in the monthly FYSPRT meetings. One of the Youth Tri-leads is building a website for youth to use for commentary. Youth meeting will be changed to see if it helps participation. | 9/23/22 Progress Update: A youth from the SOCP created and offered to share an Instagram link about youth voice for mental health during the third quarter. This link was shared with the group. The youth will be monitoring posts and will direct message (DM) those that look like they might be from youth in Thurston/Mason. Another SOCP youth is interested in research and is volunteering in that area. Neither of these youth want to be spokespersons but another youth who is a former Youth Tri-lead has volunteered to be the spokesperson and provide updates to the SOCP. 6/30/22 Progress Update: An additional Youth Tri-lead who identifies as LGBTQIA+ received a supportive vote bringing the total Youth Tri-leads to three and strengthening youth leadership. 3/31/22 Progress Update: Two new youth have been added to the roster. One youth submitted an interest statement for a Youth Tri-lead position. If the SOCP supports this youth, the SOCP would have three Youth Tri-leads and this would be a first for our FYSPRT.
Crisis services and warm handoffs after receiving crisis services. | 1. Create a crisis services matrix document. 2. Provide education and training. | 2021-04-23 | 9/24/2021 To allow time for presentations and drafts of the matrix to be presented to the group and approved. Revision: Another draft to be presented after the Administrative Services Organization board reviews the document in October. Next presentation expected at the November meeting. | 5/28/21 A. TMBHASO participant offered to draft a crisis matrix and set up a presentation by Olympic Health & Recovery Services. B. Catholic Community Crisis Stabilization Services offered a presentation and completed it at the June 25, 2021 meeting. C. Parent to get in touch with law enforcement in Mason county. By the end of Q3 2021, both children/youth's crisis and adult crisis had been presented to the SOCP. Both Thurston and Mason Sheriff's offices had presented information about the new use of force laws and how they may have an impact on crisis response. | Challenge: The issue of crisis response for youth receiving WISe was raised by families. Solution: Email to group after 5/28/21 meeting with CCS Director name and contact information for families to contact about crisis response to youth receiving WISe. Include Wise information and difference between response to crisis while receiving Wise and crisis stabilization services for youth not enrolled in WISe in CCS Crisis Stabilization Services presentation. Provide extended time for questions and answers. | Completed as of 12/31/2021 Notes: Education in the form of crisis information was presented by both children/youth and adult service providers within the second and third quarters of 2021. Thurston and Mason Sheriff's offices also provided education about the new use of force laws and their relationship with crisis response during the second and third quarters of 2021. The Crisis Clinic presented their information in the fourth quarter. The crisis matrix document was finalized in the fourth quarter and presented to the group. A vote in December 2021 of the participants resulted in closure of this Area of Focus.
More mental health awareness and fluency taught in schools, to parents and to staff. The Ending the Silence presentation with NAMI Mason/Thurston is a good starting point. | 9/23/22 After months of discussion the group may be getting closer to determining goals/action setps. The Tri-leads asked the group if they wanted host NAMI to present Ending the Silence and if after it is shared, whether they want to suggest a viewing to schools and connect them to the local Thurston/Mason NAMI representative to get it scheduled. Youth/Parents wanted the presentation. 8/26/22 The group heard from the ESD 113 Behavioral Health Navigator who explained her role that includes our regon; how students in need of behavioral health (bh) services are identified and connected to services. 7/22/22 The group discussed multiple efforts and items coming from the state education agency being implemented in schools. The Educational Service District 113 participant offered to organize the items into groups to help narrow the choices. The Tri-leads asked the convener to send out the groupings prior to the August meeting with a request for feedback. 6/24/22 The top needs were voted on by the group and ideas/action steps were identified that will be brought to the Tri-leads to determine next steps | 2022-05-27 | This is a work in progress with multiple discussions about behavioral health supports and programs being implemented in the schools in order to identify gaps and determine action steps. | The ESD 113 participant agreed to provide information and links about programs that are being implemented from the state level to the districts. She organized items into groups to help narrow the choices for the next meeting and then worked with the convener to have the ESD 113 Behavioral Health Navigator present information about her role for the group. | The challenge has been to remain focused on what the group voted for and to become educated about mental health supports already available (indicating awareness) in schools and the social emotional learning (SEL) that has been required for years. The ESD 113 has helped to move towards a solution by informing the group about what is being provided in districts by mental health providers, what the ESD provides and reminding the group about how school systems operate. The September meeting that discussed the NAMI Ending the Silence presentation highlighted educator comments about receiving so much training and exhaustion from multiple training events resulting in mention of skipping the presentation and youth/parents who were very interested in the presentation. This may have identified an information and communication gap that could bring the group closer to identifying action steps.